## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Protocol | Writing the basics of the protocol | 2:00 | 1:28 | done.
2014-10-10 | Recherche | Taking a recherche: OracleXE | 5:00 | 3:22 | required information gathered, thanks to the oracle documentation
2014-10-10 | RM-Creation | Creating the RM-Model | 1:00 | 0:42 | didn't take quite as long, thanks to the parallel creating of ER and RM
2014-10-16 | OracleXE VM | Getting started with the OracleXE Virtual Machine | 1:00 | 2:05 | ongoing
SUM |  |  | 9:00 | 7:38

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Recherche | Taking a recherche: OracleXE | 4:30 | 1:30 | still ongoing
2014-10-10 | ER-Creation | Creating the ER-Model | 1:00 | 1:40 | still ongoing
2014-10-16 | OracleXE VM | Getting started with the OracleXE Virtual Machine | 1:00 | 2:05 | ongoing
SUM |  |  | 6:30 | 5:15

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 9:00 | 7:38
| Mair | 6:30 | 5:15
| SUM | 15:30 | 12:53