## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Protocol | Writing the basics of the protocol | 2:00 | 1:28 | done.
2014-10-10 | Recherche | Taking a recherche: OracleXE | 5:00 | 3:22 | required information gathered, thanks to the oracle documentation
2014-10-10 | RM-Creation | Creating the RM-Model | 1:00 | 0:42 | didn't take quite as long, thanks to the parallel creating of ER and RM
2014-10-16 | OracleXE VM | Getting started with the OracleXE Virtual Machine | 1:00 | 2:05 | getting familiar with oraclexe wasn't 1-hour-ish
10.16.2014 | OracleXE VM | Create Script Implementation + Inserts | 2:00 | 1:30 | no comment
10.16.2014 | OracleXE VM | Creating Links and using them | 2:30 | 2:26 | no comment
10.16.2014 | OracleXE VM | Adorning the documentation | 1:00 |  | still ongoing
SUM |  |  | 14:30 | 11:33

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Recherche | Taking a recherche: OracleXE | 4:30 | 1:30 | still ongoing
2014-10-10 | ER-Creation | Creating the ER-Model | 1:00 | 1:40 | still ongoing
2014-10-16 | OracleXE VM | Getting started with the OracleXE Virtual Machine | 1:00 | 2:05 | ongoing
10.16.2014 | OracleXE VM | Create Script Implementation + Inserts | 2:00 | 1:30 | no comment
10.16.2014 | OracleXE VM | Creating Links and using them | 2:30 | 2:26 | no comment
SUM |  |  | 11:00 | 9:11

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 14:30 | 11:33
| Mair | 11:00 | 9:11
| SUM | 25:30 | 20:44