## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Protocol | Writing the basics of the protocol | 2:00 | 1:28 | done.
2014-10-10 | Recherche | Taking a recherche: OracleXE | 5:00 | 1:00 | still ongoing
2014-10-10 | RM-Creation | Creating the RM-Model | 1:00 | 0:42 | still ongoing
SUM |  |  | 8:00 | 3:10

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-10 | Recherche | Taking a recherche: OracleXE | 4:30 | 1:30 | still ongoing
2014-10-10 | ER-Creation | Creating the ER-Model | 1:00 | 1:40 | still ongoing
SUM |  |  | 5:30 | 3:10

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 8:00 | 3:10
| Mair | 5:30 | 3:10
| SUM | 13:30 | 6:20